## Product Backlog
Project Name | Tricentis
Client | Tricentis
Created By | Ankita Bakale
Creation Date | 2024-06-08
Approval Date
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
EPIC_01 | US_04 | user should be able to select automobile tab from the tops once selected below field and validation should happen for enter Product details. | Validate enter product details tab for automobile tab. | Done | 1) Start Date : : it should have a date picker and user can manually enter the date. and * sign beside it to represent mandatory field. Once hover * sign it should give a message “This field is mandatory”. user can only select the date from the future. If date is selected in back date or less then current date+30 days in future. It will give error “Must be more than one month in the future”. 2) Insurance Sum [$] : : It is a mandatory dropdown where you will find the list of car maker and * sign beside it to represent mandatory field. Once hover * sign it should give a message “select the option”. 3) Damage Insurance : It is a mandatory dropdown where you will find the list of car maker and * sign beside it to represent mandatory field. Once hover * sign it should give a message “select the option”. 4) Optional Products: it is a mandatory field. With checkbox functionality where user can select multiple option and one check box is mandatory to be selected if not then you will get a message “select at least 1 option”. Checkboxes are: Euro protection, legal Defence Insurances. 5) Merit ratings (Only Automobile) : : It is a mandatory dropdown where you will find the list of car maker and * sign beside it to represent mandatory field. Once hover * sign it should give a message “select the option” 6) Courtesy Car (Only Automobile) : : It is a mandatory dropdown where you will find the list of car maker and * sign beside it to represent mandatory field. Once hover * sign it should give a message “select the option”. 7) You will be able to see next and previous button if you click on next it will move to Select Price option if click on previous screen it should move to Enter insurant details.

## Sprint Planning
@
Project Name | Tricentis
Client | Tricentis
Created By | Ankita Bakale
Attendees | 2024-06-08
Creation Date
Epic | User Story ID | Feature/Title | User Story | Sprint
Ep_01 | US_04 | user should be able to select automobile tab from the tops once selected below field and validation should happen for enter Product details. | Validate enter product details tab for automobile tab. | 1
Story Points | Hours
1 | 1 Day
0,1, 1, 2, 3, 5, 8 | Fibinacci series

## Test scenarios
Project- Tricentis Vehicle Insurance Application.
Project Name | Tricentis
Module Name | Tricentis
Requirement Number | NA
Test case Type | Functionality Testing
Reference Doccument | NA
Pre-condition | Tricentis URL should be accessible
Test Data | : Enter Vehicle Data (tricentis.com)
Test Senario number | Description
User Story-5 Ankita Govindsa Bakale
TC_001 | Validate System navigates to Enter Product details on clicking on it.
TC_002 | Validate Start Date Functionalities.
TC_003 | Validate Insurance sum Functionalities.
TC_004 | Validate Merit Ratings Field.
TC_005 | Validate Damage Insurance Funcationalities.
TC_006 | Validate Optional Products Field Functionalities.
TC_007 | Validate Courtesy Field.
TC_008 | Validate Prev/Next buttons.
TC_009 | Validate that entered details are saved on clicking next and previous buttons.
TC_010 | Validate that on entering valid data The * sign changes to Tick sign.
TC_011 | Validate that the number of details entered is displayed beside "Enter Product details" in the Navbar.

## Test cases
User Story-5 Ankita Govindsa Bakale
Test Case Number | Test Case Name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | priority | Tested By | Test Status | Test Creation Date | Test Execution Date
TC_001 | Enter Product details page Validation | Check that on clicking "Enter product details" from the Navigation bar navigates to "Enter product details" page. | 1) Go to Tricentis Application. 2) Click on "Enter Product Details" | _ | "Enter Product details" page should be opened. | "Enter Product Details" page is opened. | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
TC_002 | Start Date Field Validation. | Check that Start date field is available and has a date picker option working properly. | 1) Go to "Enter Product details " page. 2) Check if Start Date field is available. 3) click on the small calander icon. 4) Select a date from the shown calander. | _ | User should be able to see the Start Date field and should be able to select a date from the calander provided. | User is able to see the Start Date field and is able to select a date from the calander provided. | Medium | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | check that user can manually enter the date in start date field. | 1) Go to "Enter Product details " page. 2) Enter the date manually. | 07/27/2024 | User should be able to enter the date manually. | User is able to enter the date manually. | Medium | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check for Manually Entered date if in proper format.(MM/DD/YYYY) | 1) Go to "Enter Product details " page. 2) Enter the date manually. | 07/27/2024 | It should accept the date entered. | It accepts the date entered. | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check for Manually Entered date if in improper format.(DD/MM/YYYY) | 1) Go to "Enter Product details " page. 2) Enter the date manually. | 27/07/2024 | It should not accept the date entered. | It is not accepting the date entered. | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check the beaviour Start date Field on adding Past Date. | 1) Go to "Enter Product details " page. 2) Enter the date from past. | 05/14/2024 | It should not accept the date entered and should display a message "Must be more than one month in future". | It is not accepting the date entered and displays a message "Must be more than one month in future". | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check the beaviour Start date Field on adding Current Date. | 1) Go to "Enter Product details " page. 2) Enter the present date | 2024-10-06 | It should not accept the date entered and should display a message "Must be more than one month in future". | It is not accepting the date entered and displays a message "Must be more than one month in future". | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check the beaviour Start date Field on adding Future Date but less than a month. | 1) Go to "Enter Product details " page. 2) Enter future date less than a month | 07/01/2024 | It should not accept the date entered and should display a message "Must be more than one month in future". | It is not accepting the date entered and displays a message "Must be more than one month in future". | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check the beaviour Start date Field on adding Future Date more than a month. | 1) Go to "Enter Product details " page. 2) Enter future date more than a month | 07/16/2024 | It should accept the date entered. | It is accepting the date entered. | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check the beaviour Start date Field neither with selecting any date nor entering date manually. | 1) Go to "Enter Product details " page. 2) leave start Date blank | _ | It should not allow to go for next page and display a message "Please, complete the first three steps to see the price table." | It does not allow to go for next page and displaying a message "Please, complete the first three steps to see the price table." | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check that on hovering * sign displayes a message "This field is mandatory" | 1) Go to "Enter Product details " page. 2) Hover the mouse on * sign. | _ | It should display the message "This field is mandatory". | It is not displaying the message "This field is mandatory" on hovering * sign. | Low | Low | Ankita | Fail | 2024-06-10 | 2024-06-10
|  | Check that on clicking * sign displayes a message "This field is mandatory" | 1) Go to "Enter Product details " page. 2) Click on * sign. | _ | It should display the message "This field is mandatory". | It is displaying the message "This field is mandatory". | Low | Low | Ankita | Pass | 2024-06-10 | 2024-06-10
TC_003 | Insurance sum Field Validation | Check that Insaurance sum field is available and has a dropdown working properly. | 1) Go to "Enter Product details " page. 2) Check if Insaurance sum field is available with the dropdown option. 3) Select the Insurance amount from the dropdown. | _ | User should be able to see the Insurance sum field and should be able to select amount from the dropdown provided. | User is able to see the Insurance sum field and is able to select amount from the dropdown provided. | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check that on clicking * sign displayes a message "select an option" | 1) Go to "Enter Product details " page. 2) Click on * sign. | _ | It should display the message "select an option". | It is displaying the message "select an option". | Low | Low | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check if no option is selected from the dropdown. | 1) Go to "Enter Product details " page. 2) do not select any option from the dropdown. | _ | It should not allow to go for next page and display a message "Please, complete the first three steps to see the price table." | It does not allow to go for next page and displaying a message "Please, complete the first three steps to see the price table." | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check if amount can be added manually or not. | 1) Go to "Enter Product details " page. 2) Try to enter the amount manually. | 4.000.000,00 | User should be able to enter amount manually. | User is not able to enter the amount manually. | Low | Medium | Ankita | Fail | 2024-06-10 | 2024-06-10
TC_004 | Merit Rate field Validation. | Check that Merit Rate field is available and has a dropdown working properly. | 1) Go to "Enter Product details " page. 2) Check if Merit Rate field is available with the dropdown option. 3) Select the Merit Rate from the dropdown. | _ | User should be able to see the Merit Rate field and should be able to select Rate from the dropdown provided. | User is able to see the Merit Rate field and is able to select Rate from the dropdown provided. | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check that on clicking * sign displayes a message "select an option" | 1) Go to "Enter Product details " page. 2) Click on * sign. | _ | It should display the message "select an option". | It is displaying the message "select an option". | Low | Low | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check if no option is selected from the dropdown. | 1) Go to "Enter Product details " page. 2) do not select any option from the dropdown. | _ | It should not allow to go for next page and display a message "Please, complete the first three steps to see the price table." | It does not allow to go for next page and displaying a message "Please, complete the first three steps to see the price table." | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check if Merit Rate can be added manually or not. | 1) Go to "Enter Product details " page. 2) Try to enter the Merit Rate manually. | Malus 18 | User should be able to enter Merit Rate manually. | User is not able to enter the Merit Rate manually. | Low | Medium | Ankita | Fail | 2024-06-10 | 2024-06-10
TC_005 | Damage Insurance Field Validation. | Check that Damage Insaurance field is available and has a dropdown working properly. | 1) Go to "Enter Product details " page. 2) Check if Damage Insaurance field is available with the dropdown option. 3) Select the Damage type from the dropdown. | _ | User should be able to see the Damage Insurance field and should be able to select Damage type from the dropdown provided. | User is able to see the Damage Insurance field and is able to select Damage type from the dropdown provided. | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check that on clicking * sign displayes a message "select an option" | 1) Go to "Enter Product details " page. 2) Click on * sign. | _ | It should display the message "select an option". | It is displaying the message "select an option". | Low | Low | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check if no option is selected from the dropdown. | 1) Go to "Enter Product details " page. 2) do not select any option from the dropdown. | _ | It should not allow to go for next page and display a message "Please, complete the first three steps to see the price table." | It does not allow to go for next page and displaying a message "Please, complete the first three steps to see the price table." | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check if Damage type can be added manually or not. | 1) Go to "Enter Product details " page. 2) Try to enter the Damage type manually. | Partial coverage | User should be able to enter Damage type manually. | User is not able to enter the Damage type manually. | Low | Medium | Ankita | Fail | 2024-06-10 | 2024-06-10
TC_006 | Optional Products Field Validation. | Check that Optional Products field is available and has Checkboxes working properly. | 1) Go to "Enter Product details " page. 2) Check if Optional Products field is available with the checkboxes. 3) Select an option from the given options. | _ | User should be able to see the Optional Products field and should be able to select an option from the checkboxes provided. | User is able to see the Optional Products field and is able to select an option from the checkboxes provided. | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check that on clicking * sign displayes a message "select atleast 1 option" | 1) Go to "Enter Product details " page. 2) Click on * sign. | _ | It should display the message "select atleast 1 option". | It is displaying the message "select atleast 1 option". | Low | Low | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check that user should be able to select both options. | 1) Go to "Enter Product details " page. 2) Click on both the check boxes. | _ | User should be able to select both the options. | User is not able to select both options | Low | High | Ankita | Fail | 2024-06-10 | 2024-06-10
|  | Check if no option is selected from the given options. | 1) Go to "Enter Product details " page. 2) do not select any option. | _ | It should not allow to go for next page and display a message "Please, complete the first three steps to see the price table." | It does not allow to go for next page and displaying a message "Please, complete the first three steps to see the price table." | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
TC007 | Courtesy Car Field Validation | Check that Courtesy Car field is available and has a dropdown working properly. | 1) Go to "Enter Product details " page. 2) Check if Courtesy Car field is available with the dropdown option. 3) Select an option from the dropdown. | _ | User should be able to see the Courtesy Car field and should be able to select an option from the dropdown provided. | User is able to see the Courtesy Car field and is able to select an option from the dropdown provided. | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check that on clicking * sign displayes a message "select an option" | 1) Go to "Enter Product details " page. 2) Click on * sign. | _ | It should display the message "select an option". | It is displaying the message "select an option". | Low | Low | Ankita | Pass | 2024-06-10 | 2024-06-10
|  | Check if no option is selected from the dropdown. | 1) Go to "Enter Product details " page. 2) do not select any option from the dropdown. | _ | It should not allow to go for next page and display a message "Please, complete the first three steps to see the price table." | It does not allow to go for next page and displaying a message "Please, complete the first three steps to see the price table." | High | High | Ankita | Pass | 2024-06-10 | 2024-06-10
TC008 | Prev/Next Button Validation. | Check if Prev/Next button is available. Check that Prev button navigates to previous page. Check that Next button navigates to the next page | 1) Go to "Enter Product details " page. 2) Check that Prev button is visible, click on prev/button 3) Check that next button is visible, click on Next button. | _ | User should be able to see Prev and Next buttons and both the buttons should be navigating to appropreate pages.(Prev to previous page and Next to Next page) | User is able to see Prev and Next buttons and both the buttons are navigating to appropreate pages. (Prev to previous page and Next to Next page) | Low | Low | Ankita | Pass | 2024-06-10 | 2024-06-10
TC009 | Validate the Entered Details are Saved or not. | Check that on Entering all the details and ckicking on Prev/Next button, the data entered must be saved. | 1) Go to "Enter Product details " page. 2) Enter the Date. 3) Enter the Insurance sum. 4) Enter the Merit Rating. 5) Enter Damage Insurance. 6) Enter Optional Products. 7) Enter Courtesy Car. 8) Click on Prev button. 9) Go to "Enter Product details " page. 10) click on Next Button. 11) Go to "Enter Product details " page. | 2) 08/12/2024 3) 3.000.000,00 4)Malus 17 5) Partial coverage 4) Euro Protection 5)Yes | All the entered Data must be saved . | All the entered data is not saved. User has to re enter the data. | High | High | Ankita | Fail | 2024-06-10 | 2024-06-10
TC010 | Validate the changes of * sign | Check that the * sign Changes to tick mark only on Entering correct data in all the fields. | 1) Go to "Enter Product details " page. 2) Enter the Date. 3) Enter the Insurance sum. 4) Enter the Merit Rating. 5) Enter Damage Insurance. 6) Enter Optional Products. 7) Enter Courtesy Car. 8) Click on Prev button. 9) Go to "Enter Product details " page. 10) click on Next Button. 11) Go to "Enter Product details " page. | 2) 12-07-2024 3) 3.000.000,00 4)Malus 17 5) Partial coverage 4) Euro Protection 5)Yes | The * sign should change to tick mark sign on entering correct data in all the fields. | The * sign changes to tick mark sign on entering correct data in all the fields. | Low | Medium | Ankita | Pass | 2024-06-10 | 2024-06-10
TC011 | Validate number of details entered in the navbar beside "Enter Product details" | Validate that the initial number of details to be entered is 6 and it changes based the number of fields entered | 1) Go to "Enter Product details " page. 2) Enter the Date. 3) Enter the Insurance sum. 4) Enter the Merit Rating. 5) Enter Damage Insurance. 6) Enter Optional Products. | 2) 12-07-2024 3) 3.000.000,00 4)Malus 17 5) Partial coverage 4) Euro Protection | The number of details to enter should be changed from 6 to 1 . As 1 field is left to enter. | The number of details to enter is changed from 6 to 1. As 1 field is left to enter. | Low | Low | Ankita | Pass | 2024-06-10 | 2024-06-10

## Test excution details
Test case number | test case name | screen shorts
TC_001 | Enter Product details page Validation
TC_002 | Start Date Field Validation.
TC_003 | Insurance sum Field Validation
TC_004 | Merit Rate field Validation.
TC_005 | Damage Insurance Field Validation.
TC_006 | Optional Products Field Validation.
TC007 | Courtesy Car Field Validation
TC008 | Prev/Next Button Validation.
TC009 | Validate the Entered Details are Saved or not.
TC010 | Validate the changes of * sign
TC011 | Validate number of details entered in the navbar beside "Enter Product details"

## Defects
User Story-5 Ankita Govindsa Bakale
Defect Number | Project Name | Module Name | Requirement | Test Case ID | Summary | Description | Issues | Severity | Priority | Assigned By
DC_01 | Tricentis | Tricentis | NA | TC_002 | Check that on hovering * sign displayes a message "This field is mandatory" | Steps to Reproduce : 1) Go to "Enter Product details " page. 2) Hover the mouse on * sign. Environment Result: 1. OS: Windows 10 2. Browser: Version Firefox 126 3: English. | On hovering * sign no message is displayed. | Low | Low | Ankita
DC_02 | Tricentis | Tricentis | NA | TC_003 | Check if amount can be added manually or not in "Insurance sum field. | Steps to Reproduce : 1) Go to "Enter Product details " page. 2) Try to enter the amount manually in Insurance sum field. Environment Result: 1. OS: Windows 10 2. Browser: Version Firefox 126 3: English. | User is not able to add Insurance Sum amount manually, only the amount given in the dropdown can be selected. | Low | Medium | Ankita
DC_03 | Tricentis | Tricentis | NA | TC_004 | Check if Merit Rate can be added manually or not. | Steps to Reproduce : 1) Go to "Enter Product details " page. 2) Try to enter the Merit Rate manually. Environment Result: 1. OS: Windows 10 2. Browser: Version Firefox 126 3: English. | User is not able to enter the Merit Rate manually. only the Ratings given in the dropdown can be selected. | Low | Medium | Ankita
DC_04 | Tricentis | Tricentis | NA | TC_005 | Check if Damage type can be added manually or not. | Steps to Reproduce : 1) Go to "Enter Product details " page. 2) Try to enter the Damage type manually. Environment Result: 1. OS: Windows 10 2. Browser: Version Firefox 126 3: English. | User is not able to enter the Damage Type manually. only the Types given in the dropdown can be selected. | Low | Medium | Ankita
DC_05 | Tricentis | Tricentis | NA | TC_005 | Check that user should be able to select both options. | Steps to Reproduce : 1) Go to "Enter Product details " page. 2) Click on both the check boxes. Environment Result: 1. OS: Windows 10 2. Browser: Version Firefox 126 3: English. | User is not able to select both the checkboxes, only one checkbox can be selected from the given options. | Low | High | Ankita
DC_06 | Amazon | Amazon | NA | TC_009 | Check that on Entering all the details and ckicking on Prev/Next button, the data entered must be saved. | Steps to Reproduce : 1) Go to "Enter Product details " page. 2) Enter the Date. 3) Enter the Insurance sum. 4) Enter the Merit Rating. 5) Enter Damage Insurance. 6) Enter Optional Products. 7) Enter Courtesy Car. 8) Click on Prev button. 9) Go to "Enter Product details " page. 10) click on Next Button. 11) Go to "Enter Product details " page. Environment Result: 1. OS: Windows 10 2. Browser: Version Firefox 126 3: English. | All the entered data is not saved once Prev/Next button is clicked. | High | High | Ankita

## Defect_Snapshots
User Story-5 Ankita Govindsa Bakale
Defect number Test case ID Summary Snapshots
DC_01 | TC_002 | Check that on hovering * sign displayes a message "This field is mandatory"
DC_02 | TC_003 | Check if amount can be added manually or not in "Insurance sum field.
DC_03 | TC_004 | Check if Merit Rate can be added manually or not.
DC_04 | TC_005 | Check if Damage type can be added manually or not.
DC_05 | TC_005 | Check that user should be able to select both options.
DC_06 | TC_009 | Check that on Entering all the details and ckicking on Prev/Next button, the data entered must be saved.

## Story_Point_Effort_and_Reason
User Story-5 Ankita Bakale
Project Name :- | Tricentis
Story Point :- | 3
Reason for story point :- | user should be able to select automobile tab from the tops once selected below field and validation should happen for enter Product details.
Efforts(in hours) :- | 8
Reason for Efforts :- | Test Senario and Test cases creation - 6 Test Execution - 1 Rising Bugs - 1

## Test report
SNO | User Story | PASS | FAIL | BLOCKERS | NOT EXECUTED | TOTAL TEST CASE | PASS RATIO (%) | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
1 | User story 4: Ankita Bakale | 29 | 6 | 0 | 0 | Total- 11 Sub-35 | 82.85 | 0 | 6 | 35 | 6